## Sheet1
Key
Anna
Alyssa
Avi
Jacob
All
Week
| Group Member Assigned | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Problem Statement | Anna | bar: Week 2
Use Cases | All | bar: Week 2
Project Elicitation | bar: Week 3
Functional Requirements | bar: Week 3
Design DB | Jacob | bar: Week 5 to Week 6
Build DB | Jacob | bar: Week 5 to Week 6
Create GUI markup | Anna | bar: Week 1 to Week 2
Create database outline | bar: Week 3 to Week 4
Lab 3 | bar: Week 3
Create homescreen | Anna
Create profile screen | Anna
create file upload | Anna
create resources page | Anna
Learn nodejs | All | bar: Week 1 to Week 3
setup database
prompt engineering | Avi | bar: Week 3 to Week 5
Set up Github | Jacob | bar: Week 2
Submit group project description | Avi | bar: Week 3 to Week 5
Create progress report 1 | bar: Week 4 to Week 6
Mid-semster peer evaluation | All
Progress report 2
Create documentation | Avi | bar: Week 4 to Week 8
end of semester peer evaluation
Final presentation
page to track symptoms | Anna | bar: Week 6
Page for medical professionals | Anna | bar: Week 7